## Slide 1: Status Report: Coordinated Gameplaying Robots
Project By:
Anuj Gautam (069/BEX/404)
Dilip Paneru (069/BEX/413)
Ramesh Neupane (069/BEX/433)
Yesh Kumar Adhikari (069/BEX/447)

## Slide 2: Project Overview
Coordinated Gameplaying Robots
Multiple Robots working in a coordinated manner to play football.

## Slide 3: Progress Overview
Expected delivery
September 1, 2016
Recent progress
Ball position and velocity tracking
Hardware Implementation
Biggest problem
Real-time requirement of the project.

## Slide 4: Progress - Software
Ball Position and Velocity Tracking (2D)
The calibrated ball in a controlled environment can be tracked
The program can further find out its velocity

## Slide 5: Ball Tracking
Feature extraction of the ball

## Slide 6: Progress - Hardware
Implementation of the Platform
The mobile platform needed for the project has been implemented
Platform currently works as an open-loop system

## Slide 7: Attention areas
Communication System
RF communication seems unfeasible
Wi-Fi communication causes time-lag
Motor Precision
Slippage errors occur even when using rotary encoders
IMU introduces drift errors in the system
Camera has low resolution for error correction

## Slide 8: Schedule

## Slide 9
Completed
Study and Research
15.05.2016
Image Processing (70%)
15.06.2016
Hardware Prototype (30%)
01.07.2016
Product Prototype
01.09.2016
Complete Product

## Slide 10: Gantt Chart

## Slide 11: Next steps
Hardware Control System
An implementation of control algorithms(PID) and sensor fusion for feedback based precise hardware control.
Learning System
The learning module by which the robots learn utilizing a certain fitness function
Integration, Testing and Debugging
Integration of different parts of the project and their testing and debugging to bring forth a complete product.

## Slide 12: Thank You!
Any Questions?